## Summary
Screen / Test cases |  | Total time
|  | Low(hr) | Medium(hr) | High(hr) | Status
1 | New Campaign | 0 | 0 | 0 | Completed
2 | New Campaign Status Count(Selection screen) | 0 | 0 | 0 | Completed
3 | New Campaign (No Default Mailer) - General Tab | 76 | 114 | 152 | Inprogress
4 | Edit Campaign - General Tab | 33 | 48 | 66
5 | Edit Campaign - Reports (Pivot) | 88 | 132 | 176
6 | Edit Campaign - Reports (Multi Dimensional) | 48 | 72 | 96
7 | Edit Campaign - Max Per | 72 | 108 | 144
8 | Edit Campaign - Output | 144 | 216 | 288
9 | Edit Campaign - Billing | 40 | 60 | 80
10 | Edit Campaign - Documents | 56 | 84 | 112
11 | Edit Campaign - Seeds | 96 | 144 | 192
12 | Sources | 68 | 102 | 136
13 | New Segment | 76 | 114 | 152
14 | Edit Segment | 56 | 84 | 112
15 | Copy Segment | 80 | 120 | 160
16 | Delete Segment | 52 | 78 | 104
17 | Move Segment | 68 | 102 | 136
18 | Campaign History | 92 | 138 | 184
Total |  | 1145 | 1716 | 2290
Total(Days) |  | 174 | 260 | 348
Total(Months) |  | 8.5 months | 12.5 months | 17 months

## Camapign and Selection screen
Work Estimation Details |  |  |  | Development/Construction
Sr. No. | Activity/Task/Feature Description |  | Complexity | Low(hr) | Medium(hr) | High(hr) | Steps | Story point | Sprint | Status
1 | New Campaign
| 1 | Verify a proper error message is displayed when the Description is left blank on Save | Low |  |  |  | 2 | 1 | Sprint 7 | Completed
| 2 | Verify a proper error message is displayed when the Description is over 50 chars | Low |  |  |  | 2 | 1 | Sprint 7 | Completed
| 3 | Verify the default Campaign Description appear correctly | Low |  |  |  | 2 | 1 | Sprint 7 | Completed
| 4 | Verify New Campaign screen pops up on clicking "New Campaign" | Low |  |  |  | 2 | 1 | Sprint 7 | Completed
| 5 | Verify Offer is blank by default | Low |  |  |  | 1 | 1 | Sprint 7 | Completed
| 6 | Verify "Net" is selected by default | Low |  |  |  | 1 | 1 | Sprint 7 | Completed
| 7 | Verify on Save a New Campaign is created successfully with Net Radio button | Low |  |  |  | 5 | 2 | Sprint 7 | Completed
| 8 | Verify on Save a New Campaign is created successfully with Gross Radio button | Low |  |  |  | 5 | 2 | Sprint 7 | Completed
| 9 | Verify Cancel button it should not create new campaign. | Low |  |  |  | 5 | 2 | Sprint 7 | Completed
| 10 | Verify on Save a New Campaign is created successfully | Low |  |  |  | 10 | 2 | Sprint 7 | Completed
| 11 | Verify Database, Description, Offer and Gross radio button should saved correctly | Low |  |  |  | 10 | 3 | Sprint 8 | Completed
| 12 | Verify Database, Description, Offer and Net radio button should saved correctly | Low |  |  |  | 10 | 3 | Sprint 8 | Completed
| 13 | Verify that Campaign List screen shows no data for the databases users have no access to | Low |  |  |  | 3 | 1 | Sprint 8 | Completed
| 14 | Verify that Campaign List screen shows data for the databases users have access to | Low |  |  |  | 3 | 1 | Sprint 8 | Completed
| 15 | Verify that Campaign List screen shows no data for the security groups users have no access to | Low |  |  |  | 3 | 1 | Sprint 8 | Completed
| 16 | Verify that Campaign List screen shows data for the security group users have access to | Low |  |  |  | 3 | 1 | Sprint 8 | Completed
| 17 | Verify that in advanced search ID field functionality works | Low |  |  |  | 7 | 1 | Sprint 8 | Completed
| 18 | Verify that in advanced search description field functionality works | Low |  |  |  | 7 | 1 | Sprint 8 | Completed
| 19 | Verify that in advanced search status field functionality works | Low |  |  |  | 7 | 1 | Sprint 8 | Completed
| 20 | Verify that in advanced search status date (date picker) functionality works | Low |  |  |  | 7 | 1 | Sprint 8 | Completed
| 21 | Verify that in advanced search combination of id,description,status and status date functionality works | Low |  |  |  | 7 | 1 | Sprint 8 | Completed
| 22 | Verify that when we put campaign id both on advance search and normal search it should show proper output functionality works | Low |  |  |  | 7 | 1 | Sprint 8 | Completed
| 23 | Verify that search functionality works | Low |  |  |  | 6 | 2 | Sprint 8 | Completed
| 24 | Verify system doesnt break when single quotes is entered in campaign description or offer | Low |  |  |  | 2 | 1 | Sprint 9 | Completed
| 25 | Verify search doesnt break when single quotes are entered in search values | Low |  |  |  | 2 | 1 | Sprint 9 | Completed
| 26 | Verify that grid is refreshed after saving new campaign | Low |  |  |  | 3 | 2 | Sprint 9 | Completed
| 27 | Select duration for displaying campaign | Low |  |  |  | 2 | 2 | Sprint 9 | Completed
| Total |  |  | 0 | 0 | 0 | 124 | 38
2 | New Campaign Status Count(Selection screen)
| 1 | Verify that the values "New Segment", "Copy", "Edit", "Execute" and "Print" appear in the Action drop down at "10: Count Created" status | Low |  |  |  | 4 | 2 | Sprint 9 | Completed
| 2 | Verify that the values "New Segment", "Copy", "Edit", "Cancel" and "Print" appear in the Action drop down at "20: Count Submitted" status | Low |  |  |  | 5 | 2 | Sprint 9 | Completed
| 3 | Verify that the values "New Segment", "Copy", "Edit" and "Print" appear in the Action drop down at "30: Count Running" status | Medium |  |  |  | 5 | 2 | Sprint 10 | Completed
| 4 | Verify that the values "New Segment", "Copy", "Edit", "Output" and "Print" appear in the Action drop down at "40: Count Completed" status | Medium |  |  |  | 7 | 3 | Sprint 10 | Completed
| 5 | Verify that the values "New Segment", "Copy", "Edit", "Cancel" and "Print" appear in the Action drop down at "70: Output Submitted" status | High |  |  |  | 13 | 5 | Sprint 10 | Completed
| 6 | Verify that the values "New Segment", "Copy", "Edit", "Ship" and "Print" appear in the Action drop down at "90: Output Completed" status. | High |  |  |  | 14 | 5 | Sprint 11 | Completed
| 7 | Verify that the values "New Segment", "Copy", "Edit" and "Print" appear in the Action drop down at "110: Approved for Shipping" status. | High |  |  |  | 16 | 5 | Sprint 12 | Completed
| 8 | Verify that the values "New Segment", "Copy", "Edit" and "Print" appear in the Action drop down at "120: Waiting to Ship" status. | High |  |  |  | 17 | 5 | Sprint 12 | Completed
| 9 | Verify that the values "New Segment", "Copy", "Edit" and "Print" appear in the Action drop down at "140: Shipment Failed" status. | High |  |  |  | 17 | 5 | Sprint 12 | Completed
| 10 | Verify that the values "New Segment", "Copy", "Edit" and "Print" appear in the Action drop down at "130: Shipped" status. | High |  |  |  | 17 | 5 | Sprint 13 | Completed
| 11 | Verify that the values "New Segment", "Copy", "Edit", "Cancel" and "Print" appear in the Action drop down at "100: Output Failed" status. | High |  |  |  | 14 | 3 | Sprint 13 | Completed
| 12 | Verify that the values "New Segment", "Copy", "Edit" and "Print" appear in the Action drop down at "150: Cancelled" status. | Low |  |  |  | 8 | 2 | Sprint 13 | Completed
| 13 | Verify that the created campaign should reach "10:Count Created" to "130:Shipped’successfully". | Medium |  |  |  | 15 | 3 | Sprint 13 | Completed
| 14 | Verify a proper error message is displayed when the "Ship to" is not selected in shipping section output tab. | Medium |  |  |  | 8 | 2 | Sprint 14 | Completed
| 15 | Verify a proper error message is displayed when the invalid email id is enterd in "Ship to" and "CC" field shipping section output tab. | Medium |  |  |  | 9 | 2 | Sprint 14 | Completed
| 16 | Verify a proper error message is displayed when the "Layout" and "PO#" field is not selected in output tab and billing tab respectively. | Medium |  |  |  | 12 | 3 | Sprint 14 | Completed
| 17 | Verify a proper error message is displayed when "Sort" field is not appropriately selected as per the “layout” field. | Medium |  |  |  | 13 | 3 | Sprint 14 | Completed
| 18 | Verify a proper error message is displayed when Max per group is not selected in campaign segment. | Medium |  |  |  | 11 | 3 | Sprint 15 | Completed
| Total |  |  | 0 | 0 | 0 | 231 | 74

## Campaign(No default mailer)
Work Estimation Details |  |  |  | Development/Construction
Sr. No. | Activity/Task/Feature Description |  | Complexity | Low(hr) | Medium(hr) | High(hr) | Steps | Story point | Sprint | Status
1 | New Campaign (No Default Mailer) - General Tab
| 1 | Verify new campaign screen pops up on clicking "New Campaign". | Low |  |  |  | 5 | 1 | Sprint 16 | Completed
| 2 | Verify Database drop down is enabled. | Low |  |  |  | 6 | 1 | Sprint 16 | Completed
| 3 | Verify search works in the database drop down. | Low |  |  |  | 7 | 1 | Sprint 16 | Completed
| 4 | Verify search works with Database ID. | Low |  |  |  | 7 | 1 | Sprint 16 | Completed
| 5 | Verify search works with Database Name | Low |  |  |  | 7 | 1 | Sprint 16 | Completed
| 6 | Verify Database Dropdown shows only databases user has access to. | Low |  |  |  | 7 | 2 | Sprint 16 | Completed
| 7 | Verify the Database Dropdown values are sorted alphabetically. | Low |  |  |  | 8 | 2 | Sprint 16 | Completed
| 8 | Verify the Default database appear correctly. | Low |  |  |  | 6 | 1 | Sprint 16 | Completed
| 9 | Verify the most recently database appears as default on all new campaigns. | Low |  |  |  | 9 | 2 | Sprint 16 | Completed
| 8 | Verify the default Campaign Description appear correctly. | Low |  |  |  | 6 | 1 | Sprint 16 | Completed
| 11 | Verify Description, Customer and Broker fields are manadatory for Divisional campaigns (Ex: Database ID - 992). | Low |  |  |  | 8 | 2 | Sprint 16 | Completed
| 12 | Verify offer is not mandatory and it is a text field for Divisional campaigns (Ex: Database ID - 992). | Low |  |  |  | 7 | 2 | Sprint 17 | Completed
| 13 | Verify Description, Customer and offer fields are manadatory for Non-Divisional campaigns (Ex: Database ID - 65) | Low |  |  |  | 7 | 1 | Sprint 17 | Completed
| 14 | Verify Broker field doesn't appear for Non-Divisional campaigns (Ex: Database ID - 65). | Low |  |  |  | 6 | 1 | Sprint 17 | Completed
| 15 | Verify the correct default broker appears if the default broker is set up for the user account for Divisional campaigns (Ex: Database ID - 992). | Low | [5 empty] | Sprint 17 | Inprogress
| 14 | Verify the no default broker appears if it is not set up for the user account for Divisional campaigns (Ex: Database ID - 992). | Low | [5 empty] | Sprint 17 | Inprogress
| 17 | Verify offer field is a drop down for Non-Divisional campaigns (Ex: Database ID - 65). | Low |  |  |  | 6 | 1 | Sprint 17 | Completed
| 18 | Verify the search works when 2 or more chars and Customer id are entered in the Customer search box for Divisional campaigns (Ex: Database ID - 992). | Low | [5 empty] | Sprint 17 | Inprogress
| 19 | Verify the search works when 2 or more chars and Customer id are entered in the Customer search box for Non-Divisional campaigns (Ex: Database ID - 65). | Low | [5 empty] | Sprint 17 | Inprogress
| 20 | Verify the search works when 2 or more chars and Broker id are entered in the Broker search box for Divisional campaigns (Ex: Database ID - 992). | Low | [5 empty] | Sprint 17 | Inprogress
| 21 | Verify when a customer has only one active offer, it gets populated by default on the Offer field for Non-Divisional campaigns (Ex: Database ID - 65) | Low | 4 | 6 | 8
| 22 | Verify when a customer has more than one active offer, no offer is selected by default for Non-Divisional campaigns (Ex: Database ID - 65) | Low | 4 | 6 | 8
| 23 | Verify when a customer has more than one active offer, all the active offers appear in the drop down for Non-Divisional campaigns (Ex: Database ID - 65) | Low | 4 | 6 | 8
| 24 | Verify when selecting a different customer, the offer drop down gets updated with the offers belonging to the selected customer | Medium | 8 | 12 | 16
| 25 | Verify the Customer drop down shows all the active customers for Divisional campaigns (Ex: Database ID - 992) | Low | 4 | 6 | 8
| 26 | Verify the Broker drop down shows all the active divisional brokers for Divisional campaigns (Ex: Database ID - 992) | Low | 4 | 6 | 8
| 27 | Verify the Customer drop down shows only the customers the user has access to for Non-Divisional campaigns (Ex: Database ID - 65) | Low | 4 | 6 | 8
| 28 | Verify the search works with offer name for Non-Divisional campaigns (Ex: Database ID - 65) | Low | 4 | 6 | 8
| 29 | Verify the search works with offer ID for Non-Divisional campaigns (Ex: Database ID - 65) | Low | 4 | 6 | 8
| 30 | Verify search doesn't break with single quotes in the Database, Customer, Broker and offer drop downs for both Divisional and Non-Divisional campaigns | Medium | 8 | 12 | 16
| 31 | Verify Save button is not enabled when any of the required fields is left blank or not selected in both Divisional and Non-Divisional campaigns | Low | 4 | 6 | 8
| 32 | Verify selected Database, Customer, Broker and offer are saved properly for both Divisional and Non-Divisional campaigns | Medium | 8 | 12 | 16
| 33 | Verify selected Channel is getting saved properly for both Divisional and Non-Divisional campaigns | Medium | 8 | 12 | 16
| 34 | Verify selected Net/Gross Type is getting saved properly for both Divisional and Non-Divisional campaigns | Medium | 8 | 12 | 16
| Total |  |  | 76 | 114 | 152
2 | Edit Campaign - General Tab
| 1 | Verify New Campaign screen pops up on clicking "Edit". | Low | 3 | 4 | 6
| 2 | Verify Database drop down is disabled. | Low | 3 | 4 | 6
| 3 | Verify Database, Description, Offer, Net/Gross are populated correctly. | Low | 3 | 4 | 6
| 4 | Enter a new Description and Verify it is updated correctly on Save. | Low | 4 | 6 | 8
| 5 | Enter a new Offer and Verify it is saved successfully. | Low | 4 | 6 | 8
| 6 | Verify changes to Net/Gross are saved successfully. | Low | 4 | 6 | 8
| 7 | Verify a proper error message is displayed when the Description is left blank on Save. | Low | 4 | 6 | 8
| 8 | Verify a proper error message is displayed when the Description is over 50 chars. | Low | 4 | 6 | 8
| 9 | Verify changes to Description, Offer and Net/Gross are updated correctly. | Low | 4 | 6 | 8
| Total |  |  | 33 | 48 | 66
3 | Edit Campaign - Reports (Pivot)
| 1 | Verify search works in Row and Column drop downs and selected Row field and column fields are saved correctly. | Medium | 8 | 12 | 16
| 2 | Verify Row only report can be defined | Medium | 8 | 12 | 16
| 3 | Verify proper validation message appears on Save for Column only field report | Medium | 8 | 12 | 16
| 4 | Verify selected Campaign/Segment level, Gross/Net are saved correctly | Medium | 8 | 12 | 16
| 5 | Verify proper validation message appears when Campaign level is selected for some special fields like "SIC 6 Digits", "Selected SIC" | Medium | 8 | 12 | 16
| 6 | Verify Save works when Segment Level is selected for the special fields like "SIC 6 Digits", "Selected SIC" | Medium | 8 | 12 | 16
| 7 | Verify Delete works | Medium | 8 | 12 | 16
| 8 | Verify Campaign status changes back to 10 from 40 on any changes on this tab | Medium | 8 | 12 | 16
| 9 | Verify Campaign status changes back to 10 from 90 on any changes on this tab | Medium | 8 | 12 | 16
| 10 | Verify Campaign status changes back to 10 from 80 on any changes on this tab | Medium | 8 | 12 | 16
| 12 | Verify this tab is read only for any status greater than 80 | Medium | 8 | 12 | 16
| Total |  |  | 88 | 132 | 176
4 | Edit Campaign - Reports (Multi Dimensional)
| 1 | Verify search works in the Fields drop down | Medium | 8 | 12 | 16
| 2 | Verify multiple fields can be selected from the drop down list and selected fields are saved correctly | Medium | 8 | 12 | 16
| 3 | Verify selected Campaign/Segment level, Gross/Net are saved correctly | Medium | 8 | 12 | 16
| 4 | Verify Delete works | Medium | 8 | 12 | 16
| 5 | Verify Campaign status changes back to 10 from 40 on any changes on this tab | Low | 4 | 6 | 8
| 6 | Verify Campaign status changes back to 10 from 90 on any changes on this tab | Low | 4 | 6 | 8
| 7 | Verify Campaign status changes back to 10 from 80 on any changes on this tab | Low | 4 | 6 | 8
| 8 | Verify this tab is read only for any status greater than 80 | Low | 4 | 6 | 8
| Total |  |  | 48 | 72 | 96
5 | Edit Campaign - Max Per
| 1 | Verify Quantify field accepts only numeric values | Low | 4 | 6 | 8
| 2 | Verify search works in the Field drop down at segment level | Low | 4 | 6 | 8
| 3 | Verify search works in the Field drop down at campaign level | Low | 4 | 6 | 8
| 4 | Verify Minimum and Maximum Quantity fields accepts only numeric values | Low | 4 | 6 | 8
| 5 | Verify proper validation message appears if Maximum Quantity entered is less than Minimum Qty | Medium | 8 | 12 | 16
| 6 | Verify proper validation message appears if a Segment level Max per field from the drop down is selected but quantity for the field is left blank and vice versa. | Medium | 8 | 12 | 16
| 7 | Verify proper validation message appears if a Campaign level Max per field from the drop down is selected but Max/Min quantity is left blank and vice versa. | Medium | 8 | 12 | 16
| 8 | Verify selected quantity and the Max per field are saved correctly at campaign level | Medium | 8 | 12 | 16
| 9 | Verify selected quantity and the Max per field are saved correctly at segment level | Medium | 8 | 12 | 16
| 10 | Verify Campaign status changes back to 10 from 40 on any changes on this tab | Low | 4 | 6 | 8
| 11 | Verify Campaign status changes back to 10 from 90 on any changes on this tab | Low | 4 | 6 | 8
| 12 | Verify Campaign status changes back to 10 from 80 on any changes on this tab | Low | 4 | 6 | 8
| 14 | Verify this tab is read only for any status greater than 80 | Low | 4 | 6 | 8
| Total |  |  | 72 | 108 | 144
6 | Edit Campaign - Output
| 1 | Verify search works in all the drop downs - Media, Type, Layout, Sort, PGP Key and Split fields. | Medium | 8 | 12 | 16
| 2 | Verify "Electronic" is default in Media drop down , "Fixed-Field" is default in Type drop down. | Low | 4 | 6 | 8
| 4 | Verify "Header Row" check box is unchecked and disabled for "Fixed-Field". | Low | 4 | 6 | 8
| 5 | Verify "Header Row" check box is checked and disabled for "Excel". | Low | 4 | 6 | 8
| 6 | Verify "Header Row" check box is checked by default and enabled for other Output types. | Low | 4 | 6 | 8
| 7 | Verify "Data File Only" and "Unzipped" are unchecked by default. | Low | 4 | 6 | 8
| 8 | Verify "Data File Only" will be checked and disabled if "Unzipped" is selected. | Low | 4 | 6 | 8
| 9 | Verify the selected Media, Type, Layout, Sort and PGP Key fields are saved correctly. | Medium | 8 | 12 | 16
| 8 | Verify entered file name is saved correctly. | Low | 4 | 6 | 8
| 11 | Verify "Header Row", "Data File Only" and "Unzipped" check/unchecks are saved correctly. | Medium | 8 | 12 | 16
| 12 | Verify Notes field accepts multi-line comments, alphanumeric and special chars. | Low | 4 | 6 | 8
| 13 | Verify entered Notes are saved properly. | Low | 4 | 6 | 8
| 14 | Verify the selected Split option is saved correctly. | Medium | 8 | 12 | 16
| 15 | Verify Parts drop down appears. | Low | 4 | 6 | 8
| 14 | Verify the selected parts gets saved correctly for Split Into N Equal parts. | Low | 4 | 6 | 8
| 17 | Verify Parts drop down and Output Qty grid appear for Split Into N parts. | Low | 4 | 6 | 8
| 18 | Verify the selected parts and output quantities are saved correctly for Split Into N parts. | Low | 4 | 6 | 8
| 19 | Verify Ship To and CC fields accept multiple emails seperated by semicolon. | Low | 4 | 6 | 8
| 20 | Verify search works in Ship To drop down by name and ID. | Low | 4 | 6 | 8
| 21 | Verify Subject field accepts alphanumeric and special chars. | Low | 4 | 6 | 8
| 22 | Verify Notes field accepts multi-line comments, alphanumeric and special chars. | Low | 4 | 6 | 8
| 23 | Verify FTP Site and User Name are populated if a ftp Ship To company name is selected. | Low | 4 | 6 | 8
| 24 | Verify FTP Site and User Name are blank if a non-ftp Ship To company name is selected. | Low | 4 | 6 | 8
| 25 | Verify FTP Site and User Name fields are always read only mode. | Low | 4 | 6 | 8
| 26 | Verify entered/selected Ship To and CC are saved correctly. | Low | 4 | 6 | 8
| 27 | Verify Subject, Notes, FTP site and User Name are saved correctly. | Low | 4 | 6 | 8
| 28 | Verify Campaign status changes back to 40 from 90 on any changes on this tab. | Medium | 8 | 12 | 16
| 29 | Verify Campaign status changes back to 40 from 80 on any changes on this tab. | Medium | 8 | 12 | 16
| 32 | Verify Campaign status stays at 40 for any changes done at status 40. | Low | 4 | 6 | 8
| 33 | Verify this tab is read only for any status greater than 80. | Low | 4 | 6 | 8
| Total |  |  | 144 | 216 | 288
7 | Edit Campaign - Billing
| 1 | Verify PO#, NextMark Order#, Mailer PO and San # fields are blank by default. | Low | 4 | 6 | 8
| 2 | Verify PO#, NextMark Order#, Mailer PO and San # fields accept alphanumeric and special chars. | Low | 4 | 6 | 8
| 3 | Verify entered PO#, NextMark Order#, Mailer PO and San # fields are saved correctly. | Low | 4 | 6 | 8
| 4 | Verify "Bill Net Order" and "No Usage" checkboxes are unchecked by default. | Low | 4 | 6 | 8
| 5 | Verify "Bill Net Order" and "No Usage" check/unchecks are saved properly. | Low | 4 | 6 | 8
| 6 | Verify PO# validation for US Dataware house campaigns ("PO# should start with DWH-"). | Low | 4 | 6 | 8
| 7 | Verify Campaign status changes back to 40 from 90 on any changes on this tab. | Low | 4 | 6 | 8
| 8 | Verify Campaign status changes back to 40 from 80 on any changes on this tab. | Low | 4 | 6 | 8
| 8 | Verify Campaign status stays at 40 for any changes done at status 40. | Low | 4 | 6 | 8
| 9 | Verify this tab is read only for any status greater than 80. | Low | 4 | 6 | 8
| Total |  |  | 40 | 60 | 80
8 | Edit Campaign - Documents
| 1 | Verify Fax Waiver form gets uploaded successfully. | Medium | 8 | 12 | 16
| 2 | Verify Large Volume Order form gets uploaded successfully. | Low | 4 | 6 | 8
| 3 | Verify Do-Not-Call Waiver form gets uploaded successfully. | Low | 4 | 6 | 8
| 4 | Verify Sample Mail Piece form gets uploaded successfully. | Low | 4 | 6 | 8
| 5 | Verify original file file gets replaced on upload of a new file for all the forms. | Medium | 8 | 12 | 16
| 6 | Verify Delete of the uploaded forms works for all the forms. | Medium | 8 | 12 | 16
| 7 | Verify Campaign status doesn't change for any uploads or deletes on this tab. | Medium | 8 | 12 | 16
| 8 | Verify upload/delete works until campaign status is 80. | Medium | 8 | 12 | 16
| 9 | Verify this tab is read only at any status greater than 80. | Low | 4 | 6 | 8
| Total |  |  | 56 | 84 | 112
9 | Edit Campaign - Seeds
| 1 | Verify "Auto" key method is selected by default, "Seed Key" textbox is disabled for "Auto" key method and "Seed Key" textbox is enabled for "Manual Seed" key method. | Medium | 8 | 12 | 16
| 2 | Verify "Seed Key1" textbox is enabled for both method and saved correctly for Auto method. | Medium | 8 | 12 | 16
| 3 | Verify Seed Key and Seed Key 1 are saved correctly for Manual key option. | Low | 4 | 6 | 8
| 4 | Verify Add/Edit screen opens up on clicking the "+" icon. | Medium | 8 | 12 | 16
| 5 | Verify Add seed works. | Medium | 8 | 12 | 16
| 6 | Verify proper warning appears if <##DK##> is missing in the seed on Add/Edit. | Medium | 8 | 12 | 16
| 7 | Verify Edit seed works. | Low | 4 | 6 | 8
| 8 | Verify the correct groups appear in the Group drop down and seeds from the selected group gets added correctly. | Medium | 8 | 12 | 16
| 9 | Verify View screen opens up automatically once seeds are added via Add Group. | Low | 4 | 6 | 8
| 10 | Verify Group name is blank for seeds added manually at campaign level. | Medium | 8 | 12 | 16
| 11 | Verify correct Group name appears for seeds via Add Group. | Medium | 8 | 12 | 16
| 12 | Verify Delete Seeds. | Low | 4 | 6 | 8
| 13 | Verify Campaign status changes back to 40 from 90 on any changes on this tab. | Low | 4 | 6 | 8
| 14 | Verify Campaign status changes back to 40 from 80 on any changes on this tab. | Low | 4 | 6 | 8
| 15 | Verify Campaign status stays at 40 for any changes done at status 40. | Low | 4 | 6 | 8
| 16 | Verify this tab is read only for any status greater than 80. | Low | 4 | 6 | 8
| Total |  |  | 96 | 144 | 192
Total Test cases |  |  | 243
Total (Hours) |  |  |  | #REF! | #REF! | #REF!
Total (Days) |  |  |  | #REF! | #REF! | #REF!
Total (Months) |  |  |  | 9 months | 13.5 months | 18 months

## Sources
Work Estimation Details |  |  |  | Development/Construction
Sr. No. | Activity/Task/Feature Description |  | Complexity | Low(hr) | Medium(hr) | High(hr) | Steps | Story point | Sprint | Status
1 | Sources
| 1 | Verify sources screen title - "Campaign Level Sources" for Campaign level, "Segment # Sources" for segment level. | Medium | 8 | 12 | 16
| 2 | Verify search works by keyword and source ID. | Low | 4 | 6 | 8
| 4 | Verify sources matching the search keyword appears in the Avaliable Sources grid. | Medium | 8 | 12 | 16
| 5 | Verify Add sources work. | Medium | 8 | 12 | 16
| 6 | Verify Delete sources work. | Medium | 8 | 12 | 16
| 7 | Verify sort works in both Available and Selected Sources grid. | Medium | 8 | 12 | 16
| 8 | Verify save works even when no data is present in the Selected Sources grid. | Low | 4 | 6 | 8
| 9 | Verify Campaign status changes back to 10 from 40 on any changes to the Sources. | Low | 4 | 6 | 8
| 10 | Verify Campaign status changes back to 10 from 50 on any changes to the Sources. | Low | 4 | 6 | 8
| 11 | Verify Campaign status changes back to 10 from 90 on any changes to the Sources. | Low | 4 | 6 | 8
| 12 | Verify Campaign status changes back to 10 from 80 on any changes to the Sources. | Low | 4 | 6 | 8
| 13 | Verify Sources link is not accessible at any status greater than 80. | Low | 4 | 6 | 8
| Total |  |  | 68 | 102 | 136

## Segment
Work Estimation Details |  |  |  | Development/Construction
Sr. No. | Activity/Task/Feature Description |  | Complexity | Low(hr) | Medium(hr) | High(hr) | Steps | Story point | Sprint | Status
1 | New Segment
| 1 | Verify # field is blank and disabled. | Low | 4 | 6 | 8
| 2 | Verify a default description appears with a correct segment number appears in the Description field. | Low | 4 | 6 | 8
| 3 | Verify Description field accepts alphanumeric and special chars. | Low | 4 | 6 | 8
| 4 | Verify Required Quantity is "All Available" by default and Required Quantity field accepts numeric values only. | Low | 4 | 6 | 8
| 5 | Verify Key Code 1 field accepts alphanumeric and special chars and Key Code 2 field accepts alphanumeric and special chars. | Low | 4 | 6 | 8
| 6 | Verify the Max Per group drop down shows values from 01 to 10. | Low | 4 | 6 | 8
| 7 | Verify Net Group # value is 1 by default and Net Group # field accepts numeric values only. | Low | 4 | 6 | 8
| 8 | Verify "Apply Default Rules" is enabled by default. | Low | 4 | 6 | 8
| 9 | Verify all the entered/selected values are saved correctly. | Low | 4 | 6 | 8
| 10 | Verify Description, Required Quantity and Net Group # are mandatory fields. | Low | 4 | 6 | 8
| 11 | Verify a new segment gets added successfully. | Low | 4 | 6 | 8
| 12 | Verify the segment grid gets updated with the new segment details. | Low | 4 | 6 | 8
| 13 | Verify Campaign status changes back to 10 from 40 on any changes to the Sources. | Low | 4 | 6 | 8
| 14 | Verify Campaign status changes back to 10 from 50 on any changes to the Sources. | Low | 4 | 6 | 8
| 15 | Verify Campaign status changes back to 10 from 90 on any changes to the Sources. | Low | 4 | 6 | 8
| 16 | Verify Campaign status changes back to 10 from 80 on any changes to the Sources. | Low | 4 | 6 | 8
| 17 | Verify New Segment link is not accessible at any status greater than 80. | Low | 4 | 6 | 8
| 18 | Verify New Segment from the Selection screen Action Menu. | Low | 4 | 6 | 8
| 19 | Verify New Segment from Campaign List -> Action Menu. | Low | 4 | 6 | 8
| Total |  |  | 76 | 114 | 152
2 | Edit Segment
| 1 | Verify correct segment number appears in the # field. | Low | 4 | 6 | 8
| 2 | Verify # field is disabled. | Low | 4 | 6 | 8
| 3 | Verify correct values are populated for all the fields. | Low | 4 | 6 | 8
| 4 | Modify each field and verify the new value gets saved correctly. | Medium | 8 | 12 | 16
| 5 | Verify the segment grid gets updated on Edit Segment. | Low | 4 | 6 | 8
| 6 | Verify Campaign status changes back to 10 from 40 on any changes to the Sources. | Low | 4 | 6 | 8
| 7 | Verify Campaign status changes back to 10 from 50 on any changes to the Sources. | Low | 4 | 6 | 8
| 8 | Verify Campaign status changes back to 10 from 90 on any changes to the Sources. | Low | 4 | 6 | 8
| 9 | Verify Campaign status changes back to 10 from 80 on any changes to the Sources. | Low | 4 | 6 | 8
| 11 | Verify Edit Segment link is not accessible at any status greater than 80. | Low | 4 | 6 | 8
| 12 | Verify Edit Segment from the Selection screen Action Menu. | Low | 4 | 6 | 8
| 13 | Verify Edit Segment from Campaign List -> Segment Grid -> Action Menu. | Low | 4 | 6 | 8
| 14 | Verify Edit Segment link doesn't appear for "0: Common Rules". | Low | 4 | 6 | 8
| Total |  |  | 56 | 84 | 112
3 | Copy Segment
| 1 | Verify copy segment works correctly by comparing the original and new segment. | Medium | 8 | 12 | 16
| 2 | Verify copy segment copies over all the segment details. | Medium | 8 | 12 | 16
| 3 | Verify copy segment copies over all the selections. | Medium | 8 | 12 | 16
| 4 | Verify copy segment with a child table field in the selection of the original segment. | Medium | 8 | 12 | 16
| 5 | Verify copy segment with an external table field in the selection of the original segment. | Medium | 8 | 12 | 16
| 6 | Verify the segment grid gets updated with the new segment details. | Medium | 8 | 12 | 16
| 7 | Verify Campaign status changes back to 10 from 40 on any changes to the Sources. | Low | 4 | 6 | 8
| 8 | Verify Campaign status changes back to 10 from 50 on any changes to the Sources. | Low | 4 | 6 | 8
| 9 | Verify Campaign status changes back to 10 from 90 on any changes to the Sources. | Low | 4 | 6 | 8
| 10 | Verify Campaign status changes back to 10 from 80 on any changes to the Sources. | Low | 4 | 6 | 8
| 12 | Verify Edit Segment link is not accessible at any status greater than 80. | Low | 4 | 6 | 8
| 13 | Verify Copy Segment from the Selection screen Action Menu. | Low | 4 | 6 | 8
| 14 | Verify Copy Segment from Campaign List -> Segment Grid -> Action Menu. | Low | 4 | 6 | 8
| 15 | Verify Copy Segment link doesn't appear for "0: Common Rules". | Low | 4 | 6 | 8
| Total |  |  | 80 | 120 | 160
4 | Delete Segment
| 1 | Verify Delete segment deletes the segment completely and confirmation message appears on clicking Delete. | Medium | 8 | 12 | 16
| 2 | Verify Delete happens on Clicking "Yes" on the confirmation. | Low | 4 | 6 | 8
| 3 | Verify Delete doesn't happen on Clicking "Cancel" on the confirmation. | Low | 4 | 6 | 8
| 4 | Verify Delete Segment link doesn't appear for "0: Common Rules". | Low | 4 | 6 | 8
| 5 | Verify the deleted segment is removed from the segment grid. | Low | 4 | 6 | 8
| 6 | Verify Campaign status changes back to 10 from 40 on any changes to the Sources. | Low | 4 | 6 | 8
| 7 | Verify Campaign status changes back to 10 from 50 on any changes to the Sources. | Low | 4 | 6 | 8
| 8 | Verify Campaign status changes back to 10 from 90 on any changes to the Sources. | Low | 4 | 6 | 8
| 9 | Verify Campaign status changes back to 10 from 80 on any changes to the Sources. | Low | 4 | 6 | 8
| 10 | Verify Edit Segment link is not accessible at any status greater than 80. | Low | 4 | 6 | 8
| 11 | Verify Delete Segment from the Selection screen Action Menu. | Low | 4 | 6 | 8
| 12 | Verify Delete Segment from Campaign List -> Segment Grid -> Action Menu. | Low | 4 | 6 | 8
| Total |  |  | 52 | 78 | 104
5 | Move Segment
| 1 | Verify Move Segment pop up opens up on click of "Move" link. | Low | 4 | 6 | 8
| 2 | Verify From, To and To Location drop downs show the segment numbers available in the campaign. | Medium | 8 | 12 | 16
| 3 | Verify a proper message is displayed when "To" value is less than "From" value. | Medium | 8 | 12 | 16
| 4 | Verify a block of segments can be moved successfully. | Medium | 8 | 12 | 16
| 5 | Verify a single segment can be moved successfully. | Medium | 8 | 12 | 16
| 6 | Verify the segment grid is reordered correctly. | Medium | 8 | 12 | 16
| 7 | Verify Campaign status changes back to 10 from 40 on any changes to the Sources. | Low | 4 | 6 | 8
| 8 | Verify Campaign status changes back to 10 from 50 on any changes to the Sources. | Low | 4 | 6 | 8
| 9 | Verify Campaign status changes back to 10 from 90 on any changes to the Sources. | Low | 4 | 6 | 8
| 10 | Verify Campaign status changes back to 10 from 80 on any changes to the Sources. | Low | 4 | 6 | 8
| 11 | Verify Move link is not accessible at any status greater than 80. | Low | 4 | 6 | 8
| 12 | Verify Move link doesn't appear in the Selection screen Action Menu | Low | 4 | 6 | 8
| Total |  |  | 68 | 102 | 136

## Campaign History
Work Estimation Details |  |  |  | Development/Construction
Sr. No. | Activity/Task/Feature Description |  | Complexity | Low(hr) | Medium(hr) | High(hr) | Steps | Story point | Sprint | Status
1 | Campaign History
| 1 | Verify search with campaign name. | Low | 4 | 6 | 8
| 2 | Verify search with a single campaign ID. | Low | 4 | 6 | 8
| 3 | Verify search works with multiple campaign IDs. | Low | 4 | 6 | 8
| 4 | Verify search doesn't bring campaigns in status 10. | Low | 4 | 6 | 8
| 5 | Verify search doesn't bring campaigns in status 50. | Low | 4 | 6 | 8
| 5 | Verify search doesn't bring campaigns older than 12 months. | Medium | 8 | 12 | 16
| 6 | Verify search doesn't bring campaigns from other databases. | Medium | 8 | 12 | 16
| 7 | Verify one or more previous campaigns can be added successfully. | Medium | 8 | 12 | 16
| 8 | Verify one or more previous campaigns can be added at segment level successfully. | Medium | 8 | 12 | 16
| 9 | Verify delete of previously added campaigns works. | Medium | 8 | 12 | 16
| 8 | Verify Include/Exclude toggle works. | Low | 4 | 6 | 8
| 11 | Verify Individual/Company match level toggle works. | Low | 4 | 6 | 8
| 12 | Verify the selected Include/Exclude and Individual/Company level gets saved correctly for each added campaigns | Medium | 8 | 12 | 16
| 13 | Verify sort works on ID and Description | Medium | 8 | 12 | 16
| 14 | Verify Cancel doesn't save the changes | Medium | 8 | 12 | 16
| Total |  |  | 92 | 138 | 184